## CAB302
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
To do | Continuous Integration / Documentation | [https://canvas.qut.edu.au/courses/19226/pages/activity-8-dot-3-practical-continuous-integration-slash-documentation?module\_item\_id=1692823](https://canvas.qut.edu.au/courses/19226/pages/activity-8-dot-3-practical-continuous-integration-slash-documentation?module_item_id=1692823 "‌") |  |  |  |  | 26 | https://trello.com/c/wdgtIExn
Doing | Styling |  |  |  | TH,JP,EK,S,R |  | 32 | https://trello.com/c/8T9rRkU1
Doing | Unit testing |  |  |  | TH,JP,EK,R,S |  | 31 | https://trello.com/c/zG6WIzCX
Doing | Sprint 3 | - Register page controller - Journal (fxml page, controller, Dao if needed, or model, unit testing) - Project (fxml page, controller, Dao if needed, unit testing) - Goal (fxml page, controller, Dao if needed, unit testing) - Budgeting (fxml page, controller, Dao if needed, unit testing) - GPA (fxml page, controller, Dao if needed, unit testing) - Navigation bar controller |  |  |  |  | 33 | https://trello.com/c/wMKdUDAg
Doing | Sprint 4 | - Experts Help page (Including fxml file, controller and DAO if necessary) - Steven - Profile Page (Including fxml file, controller and DAO if necessary) - Jun - Refactoring - Lucas - Commenting and Java Docs - Ryan - Contiguous integration - Tarek - Finishing touches for unit testing - Jun |  |  |  |  | 34 | https://trello.com/c/4uxMufmS
Completed | Think of an idea |  |  |  | EK,TH,JP,S,R |  | 2 | https://trello.com/c/acgmSykp
Completed | Brain storming | [5 empty] | 6 | https://trello.com/c/i6fjunor
Completed | Additional features | Features that can or will be added to the project. |  |  | TH,JP,EK,R,S |  | 8 | https://trello.com/c/8JIq5Ks6
Completed | Features: | - List project/homework, stuff to do - Write down your emotions, feeling - Track your average mood in a given time (weekly, fortnightly, monthly, etc) - Write down details of your project/homework. - give daily motivation in the home screen - sort projects by closest due date or highest percentage - To-Do List/Task list, writing down things to do for the day, week, assigning priority) - Goal list, writing down long term and short term goals for motivation (calculating GPA, shows how what grades user need to get in order to achieve certain GPA) as well as personal goals - GPA calculator - Timetable, or calendar, for showing deadlines and due dates. - Journal entry: writing down journal for the day etc. - Sign up & Sign in - Show GPA graph - Can upload assessment files for the future usage (resume) - A page to manage finances and keep track of spending habits. College students may need something to help them keep track of spending. - A timer to record how long you have studied for and when to take breaks - lists of mental health experts to contact if needed - sleep tracker - Check list to Mark project as finished/delayed/urgent. - A counter which keeps track of how many projects are still due to be finished. - Assignment tracker, to keep track how far along a user is in the assignment. - An assignment description, which details what needs to be done for the assignment and its criteria, and may include the teaching staff contact information in case there is an inquiry. |  |  |  |  | 11 | https://trello.com/c/s9jphT69
Completed | Make 30 user stories |  |  |  | EK,TH,JP,R,S | red | 4 | https://trello.com/c/bYUtC9Q6
Completed | Make low/medium fidelity prototype |  |  |  | TH,EK,JP,R,S |  | 5 | https://trello.com/c/ZNNRIvio
Completed | Start coding project |  |  |  | TH,JP,EK,R,S |  | 7 | https://trello.com/c/JL6LCL8X
Completed | Sprint plan |  |  |  | TH,JP,EK,R,S |  | 12 | https://trello.com/c/B9OekZ9j
Completed | Database |  |  |  | EK |  | 23 | https://trello.com/c/oGo43m77
Completed | Idea format: | 1. Student Hub 2. Workout Log |  |  |  |  | 3 | https://trello.com/c/A7C2HVmI
Completed | Sprint 2 | - Sign up fmxl page UI - Sign up page controller - Database connectivity to sqlite - User data model, user data DAO, and DAO Interface (For registering and logging user data to the database) - Register fmxl page UI - Register page controller - Main Navigation bar for navigating user to different pages - Navigation bar controller - User data Mock DAO for unit testing and unit testing code |  |  |  |  | 18 | https://trello.com/c/kwi4to1N
Completed | Program features |  |  |  | JP,TH,EK,R,S |  | 25 | https://trello.com/c/jbx3e4MZ
Completed | Controllers for UI |  |  |  | JP,TH,S |  | 22 | https://trello.com/c/l90tb4bd
Completed | Goal list page |  |  |  | EK |  | 28 | https://trello.com/c/twHIpi7K
Completed | GPA calculator page |  |  |  | R |  | 27 | https://trello.com/c/i5JzAJAO
Completed | Project list page |  |  |  | JP |  | 29 | https://trello.com/c/qEGbBGYI
Completed | Finance Page |  |  |  | TH |  | 30 | https://trello.com/c/YOqbbmVq
Completed | Journal Page |  |  |  | S |  | 21 | https://trello.com/c/fFojPP2m
Needs Review | Implementing Features |  |  |  | TH,JP,EK,R,S |  | 14 | https://trello.com/c/ydagPTAB
Needs Review | Gui |  |  |  | TH,R,S |  | 13 | https://trello.com/c/D2rFbRsa

## Archived CAB302
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
To do | [archived] Task: Sign up fmxl page UI Sign up page controller Database connectivity to sqlite User data model, user data DAO, and DAO Interface (For registering and logging user data to the database) Register fmxl page UI Register page controller Main Navigation bar for navigating user to different pages Navigation bar controller User data Mock DAO for unit testing and unit testing code | [5 empty] | 15 | https://trello.com/c/3zbr1HM6
Doing | [archived] Database Connectivity | [5 empty] | 16 | https://trello.com/c/tuH6HwYS
Doing | [archived] Sign Up page - Steven | [5 empty] | 17 | https://trello.com/c/FTbbcFEs
Doing | [archived] Sprint 2 Doing | - Sign up page controller - Steven - Database connectivity to sqlite - Lucas - Register fmxl page UI - Tarek - Register page controller - Jun - Main Navigation bar for navigating user to different pages - Ryan - Navigation bar controller - Na - User data Mock DAO for unit testing and unit testing code - Na |  |  |  |  | 19 | https://trello.com/c/9E0mjK5H
Completed | [archived] Sprint 2 Completed Tasks | - Sign up fmxl page UI - Completed - User data model, user data DAO, and DAO Interface (For registering and logging user data to the database) - Completed |  |  |  |  | 20 | https://trello.com/c/Xg13c70C
[archived] More feature ideas | [archived] More features: - To-Do List/Task lisk, writing down things to do for the day, week, assignning priority) - Goal list, writing down long term and short term goals for motivation (calculating GPA, shows how what grades user need to get in order to achieve certain GPA) as well as personal goals - Timetable, or calendar, for showing deadlines and due dates. - Journal entry: writing down jorunal for the day etc... | [5 empty] | 9 | https://trello.com/c/AFurEmFL
[archived] More feature ideas | [archived] More features: - To-Do List/Task lisk, writing down things to do for the day, week, assignning priority) - Goal list, writing down long term and short term goals for motivation (calculating GPA, shows how what grades user need to get in order to achieve certain GPA) as well as personal goals - Timetable, or calendar, for showing deadlines and due dates. - Journal entry: writing down jorunal for the day etc... | [5 empty] | 10 | https://trello.com/c/QRjZ0Qje